## Sheet1
| Task Number | Task ID | Estimated Start Hours | Hours Spent - Week 5 | Hours Spent - Week 6 | Hours Spent - Week 7 | Hours Spent - Week 8 | Hours Spent - Week 9 | Hours Spent - Week 10 | Hours Spent - Week 11 | Hours Spent - Week 12 | Hours Spent - Week 13 | Total Hours
Sprint 1 | Task 1 | ID: S-0A | 1 | 1 | [8 empty] | 1
| Task 2 | ID: S-0B | 1 | 1 | 1 | [7 empty] | 2
| Task 3 | ID: S-0C | 3 | 2 | [7 empty] | 1 | 3
| Task 4 | ID: S-0E | 1 |  | 1 | [7 empty] | 1
| Task 5 | ID: S-1A | 2 |  | 2 | 1 | [6 empty] | 3
| Task 6 | ID: S-1B | 1 |  | 1 | [5 empty] | 1 |  | 2
| Task 7 | ID: S-1C | 0.5 |  |  | 0.5 | [6 empty] | 0.5
| Task 8 | ID: S-1D | 0.5 |  |  | 0.5 | [6 empty] | 0.5
| Task 9 | ID: S-1E | 2 |  |  | 3 | [6 empty] | 3
Sprint 2 | Task 10 | ID: T-0A | 1.5 |  |  |  | 1 | [5 empty] | 1
| Task 11 | ID: T-0B | 3 |  |  |  | 2 | 2 |  |  |  |  | 4
| Task 12 | ID: T-0C | 2 |  |  |  | 2 | [5 empty] | 2
| Task 13 | ID: T-0D | 1 |  |  |  |  | 1 |  |  |  |  | 1
| Task 14 | ID: T-1A | 1 |  |  |  |  | 0.5 |  |  |  |  | 0.5
| Task 15 | ID: T-1B | 2 | [5 empty] | 3 |  |  |  | 3
| Task 16 | ID: T-1C | 1 | [5 empty] | 1 |  |  |  | 1
| Task 17 | ID: T-2A | 1 | [5 empty] | 1 | 1 |  |  | 2
| Task 18 | ID: T-2B | 3 | [6 empty] | 2 | 0.5 |  | 2.5
| Task 19 | ID: T-2C | 3 | [6 empty] | 4 |  |  | 4
| Task 20 | ID: T-2D | 1 | [6 empty] | 2 |  |  | 2
| Task21 | ID: T-3A | 1 | [7 empty] | 1 | 1 | 2
| Task 22 | ID: T-3B | 1 | [8 empty] | 2 | 2
| Task 23 | ID: T-3C | 1 | [8 empty] | 1 | 1
|  | Actual Remaining Hours |  | 34.5 | 31.5 | 27.5 | 22.5 | 19.5 | 16 | 12 | 4.5 | 3
|  | Estimated Remaing Hours |  | 34.5 | 29.5 | 25.5 | 22.5 | 15 | 13 | 9 | 2 | 0
|  | Rework |  |  | 1 | 1 |  | 2 |  | 1 | 1.5 | 1